Efektywność cząstkowa projektów naukowych  finansowanych ze środków publicznych

Słowa kluczowe: projekt, ewaluacja, efektywność, beneficjent

STRESZCZENIE

Jednym z rodzajów efektywności jest efektywność cząstkowa określana na etapie realizacji przedsięwzięcia z uwzględnieniem zaawansowania wykonania prac oraz poniesionych kosztów. Celem artykułu jest analiza narzędzi monitorowania efektywności cząstkowej projektów naukowych. Przedmiotem analizy są projekty naukowe finansowane w ramach programu NCBiR – STRATEGMED. Analiza wydatkowania środków przekazanych beneficjentom przez NCBiR została wykonana z zastosowaniem metody dynamicznej (strumieniowej), której istotą jest analiza przepływu środków pieniężnych między dwoma podmiotami. Metoda monograficzna posłużyła do analizy narzędzi monitorowania efektywności cząstkowej, umożliwiając szczegółowe zbadanie ich cech i elementów.

NCBiR dokonuje ewaluacji bieżącej, która determinuje efektywność cząstkową  na poziomie projektów realizowanych przez beneficjentów oraz holistycznie w zakresie programów sektorowych. Zarówno w ramach pierwszego jak i drugiego poziomu przyjmowane są wskaźniki produktu, sprawozdawane w raportach okresowych.

Partial effectiveness of scientific projects financed through public funds

Key words: project, evaluation, effectiveness, beneficiary

SUMMARY

One of types of effectiveness is the partial one determined at the stage of completion of undertaking, taking into account the progress of performed works and incurred costs. The objective of the article is an analysis of tools used for monitoring of partial effectiveness in scientific projects. Scientific projects financed within the STRATEGMED programme by NCRD is the subject of the analysis. An analysis of the funds disbursed transferred to beneficiaries  by NCRD, has been performed with the use of the dynamic method (streaming) which consists in an analysis of cash-flow between two subjects. The monographic method was used for an analysis of tools for monitoring partial effectiveness, enabling to examine their features and components in detail.

NCRD performs on-going evaluation which determines partial effectiveness at the project implementation stage performed by beneficiaries, as well as holistically in the scope of sector programmes. Within both first and second level, indicators for a product are adopted and reported in periodic reports.