Figure 1 Share of scientific projects carried out by individual beneficiaries in total number of scientific projects implemented over period

2011-2014 (in %)

Source Own studies on the basis of activity of NCRD for 2014, Warsaw March 2015 p. 71

Figure 2 Budget expenses in Section 730 - Science in 2014 in division according to the tasks carried out (%)

Source Own studies on the basis of the report on operations of NCRD for 2014 Warsaw March 2015 p. 18

Chart 1 Financing an action taken within the field of scientific research serving the practical use in 2015

| Item no. | Name of action | 2015 scheme (Thousand PLN) | Performance in 2015 (thousand PLN) |
| --- | --- | --- | --- |
| 1 | Financing applied research | 663,181 | 660,904 |
| 2 | Financing R+D research and commercialization of their results in subjects which have a capability of application of their results in practice | 1,632,619 | 1,178358 |
| 3 | The development of R+D staff competences and increase in awareness of a role of science in economic development | 26 948 | 24 139 |
| 4 | R+D support in the scope of the national defence | 348,737 | 346,953 |
| 5 | Financing the “Improvement of the working and safety conditions”multiannual programme - Stage 3 | 10,500 | 10,500 |
| 6 | Support creation of common infrastructure of research units | 1,850,252 | 1,748,471 |

Own studies on the basis of the report on operations of NCRD for 2015 Warsaw March 2016 p. 102-126

Chart 2 Selected product rates within STRATEGMED programme

In 2015

| Rates | Target value | The value planned In 2015 | Reached value In 2015 |
| --- | --- | --- | --- |
| Number of publications concerning the R+D works of the programme whose authors are members of research teams in periodicals included in Science Citation Index. | 200 | 15 | 6 |
| Number of new research teams formed for implementation of projects within the programme | 40 | 9 | 56 |
| Number of the patent applications in PCT and EPO mode | 50 | 1 | 3 |

Source Own studies developed on the basis of The activity report of NCRD for 2015, NCRD June 2016 p. 102-106